## MRS
Group 1 - Gantt Chart
| Group | 1 |  |  | DEPARTMENT |  |  |  | Computer Engineering
| SEMESTER | 2nd Semester |  |  | SY |  |  |  | 2025-2026
ID | TASK | START DATE | DUE DATE | STATUS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | WEEK 20
 | time axis 2025-11-29 to 2026-04-03
1 | Planning Phase
1.1 | Brainstorming | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-05
1.2 | Researching | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-05
1.3 | Conceptualization | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-05
1.4 | Searching for possible client | 2025-11-29 | 2025-12-08 | Done | bar: 2025-11-29 to 2025-12-12
1.5 | Background checking of the possible client | 2025-11-29 | 2025-12-08 | Done | bar: 2025-12-06 to 2025-12-12
2 | Requirements
2.1 | Progress Report 1 | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-12
2.2 | Progress Report 2 | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-12
2.3 | Progress Report 3 | 2025-11-29 | 2025-11-29 | Done | bar: 2025-11-29 to 2025-12-05
2.4 | Progress Report 4 | 2025-12-13 | 2025-12-13 | Done | bar: 2025-12-13 to 2026-01-24
2.5 | Progress Report 5 | 2025-12-13 | 2025-12-13 | Done | bar: 2025-12-13 to 2026-01-24
2.6 | Progress Report 6 | 2025-12-13 | 2025-12-13 | Done | bar: 2025-12-13 to 2026-01-24
2.7 | Progress Report 7 | 2026-01-24 | 2026-01-24 | Done | bar: 2026-01-25 to 2026-01-29
2.8 | Progress Report 8 | 2026-01-24 | 2026-01-24 | Done | bar: 2026-01-25 to 2026-01-29
2.9
3 | Design Phase
3.1 | Flowchart | 2025-12-13 | 2026-01-23 | Done | bar: 2025-12-13 to 2026-01-24
3.2 | DFD (Data Flow Diagram) | 2025-12-13 | 2026-01-23 | Done | bar: 2025-12-13 to 2026-01-24
3.3 | ERD (Entrity-Relationship Diagram) | 2025-12-13 | 2026-01-23 | Done | bar: 2025-12-13 to 2026-01-24
3.4 | Storyboarding | 2025-12-13 | 2026-01-23 | Done | bar: 2025-12-13 to 2026-01-24
3.5 | Algorithm | 2026-01-24 | 2026-01-29 | Done | bar: 2026-01-25 to 2026-01-29
4 | Development Phase
4.1 | HTML and PHP Coding of User Interface
4.2 | HTML and PHP Coding Front End
4.3 | HTML and PHP Coding Back End
4.4 | System Testing
4.5 | Debugging
5 | QA & Testing
5.1 | Multiple Device Test
5.2 | Beta Testing
6 | Deployment & Maintenance
6.1 | Authoring Privacy Policies and User Manual
6.2 | Deployment
6.3 | Maintenance
7 | Documentation
7.1 | Chapter 1: Introduction |  |  | Ongoing | bar: 2025-12-21 to 2025-12-25
7.2 | Chapter 2: Review of Related Literature and Studies |  |  | Ongoing
7.3 | Chapter 3: Methodology |  |  | Ongoing
7.4 | Chapter 4: Results and Discussion |  |  | Ongoing
7.5 | Chapter 5: Conclusion |  |  | Ongoing
7.6 | Final Paper Check
7.7 | Defense
LEGEND